## Basic View
ITTOs - Basic View |  |  |  |  | projectprep.org
Knowledge Area | Process Group | Process | Inputs | Tools & Techniques | Outputs
Integration Management: | Initiating | Develop Project Charter | Business Documents | Expert Judgment | Project Charter
|  |  | Agreements | Data Gathering | Assumption Log
|  |  | Enterprise Environmental Factors | Interpersonal & Team Skills
|  |  | Organizational Process Assets | Meetings
| Planning | Develop Project Management Plan | Project Charter | Expert Judgment | Project Management Plan
|  |  | Outputs from Other Processes | Data Gathering
|  |  | Enterprise Environmental Factors | Interpersonal & Team Skills
|  |  | Organizational Process Assets | Meetings
| Executing | Direct and Manage Project Work | Project Management Plan | Expert Judgment | Deliverables
|  |  | Project Documents | Project Management Information System | Work Performance Data
|  |  | Approved Change Requests | Meetings | Issue Log
|  |  | Enterprise Environmental Factors |  | Change Requests
|  |  | Organizational Process Assets |  | Project Management Plan Updates
Project Documents Updates
Organizational Process Assets Updates
| Executing | Manage Project Knowledge | Project Management Plan | Expert Judgment | Lessons Learned Register
|  |  | Project Documents | Knowledge Management | Project Management Plan Updates
|  |  | Deliverables | Information Management | Organizational Process Assets Updates
|  |  | Enterprise Environmental Factors | Interpersonal & Team Skills
Organizational Process Assets
| M&C | Monitor and Control Project Work | Project Management Plan | Expert Judgment | Work Performance Reports
|  |  | Project Documents | Data Analysis | Change Requests
|  |  | Work Performance Information | Decision Making | Project Management Plan Updates
|  |  | Agreements | Meetings | Project Documents Updates
Enterprise Environmental Factors
Organizational Process Assets
| M&C | Perform Integrated Change Control | Project Management Plan | Expert Judgment | Approved Change Requests
|  |  | Project Documents | Change Control Tools | Project Management Plan Updates
|  |  | Work Performance Reports | Data Analysis | Project Documents Updates
|  |  | Change Requests | Decision Making
|  |  | Enterprise Environmental Factors | Meetings
Organizational Process Assets
| Closing | Close Project or Phase | Project Charter | Expert Judgment | Project Documents Updates
|  |  | Project Management Plan | Data Analysis | Final Product, Service, or Result Transition
|  |  | Project Documents | Meetings | Final Report
|  |  | Accepted Deliverables |  | Organizational Process Assets Updates
Business Documents
Agreements
Procurement Documentation
Organizational Process Assets
Scope Management: | Planning | Plan Scope Management | Project Charter | Expert Judgment | Scope Management Plan
|  |  | Project Management Plan | Data Analysis | Requirements Management Plan
|  |  | Enterprise Environmental Factors | Meetings
Organizational Process Assets
| Planning | Collect Requirements | Project Charter | Expert Judgment | Requirements Documentation
|  |  | Project Management Plan | Data Gathering | Requirements Traceability Matrix
|  |  | Project Documents | Data Analysis
|  |  | Business Documents | Decision Making
|  |  | Agreements | Data Representation
|  |  | Enterprise Environmental Factors | Interpersonal & Team Skills
|  |  | Organizational Process Assets | Context Diagram
Prototypes
| Planning | Define Scope | Project Charter | Expert Judgment | Project Scope Statement
|  |  | Project Management Plan | Data Analysis | Project Documents Updates
|  |  | Project Documents | Decision Making
|  |  | Enterprise Environmental Factors | Interpersonal & Team Skills
|  |  | Organizational Process Assets | Product Analysis
| Planning | Create WBS | Project Management Plan | Expert Judgment | Scope Baseline
|  |  | Project Documents | Decomposition | Project Documents Updates
Enterprise Environmental Factors
Organizational Process Assets
| M&C | Validate Scope | Project Management Plan | Inspection | Accepted Deliverables
|  |  | Project Documents | Decision Making | Work Performance Information
|  |  | Verified Deliverables |  | Change Requests
|  |  | Work Performance Data |  | Project Documents Updates
| M&C | Control Scope | Project Management Plan | Data Analysis | Work Performance Information
|  |  | Project Documents |  | Change Requests
|  |  | Work Performance Data |  | Project Management Plan Updates
|  |  | Organizational Process Assets |  | Project Documents Updates
Schedule Management: | Planning | Plan Schedule Management | Project Charter | Expert Judgment | Schedule Management Plan
|  |  | Project Management Plan | Data Analysis
|  |  | Enterprise Environmental Factors | Meetings
Organizational Process Assets
| Planning | Define Activities | Project Management Plan | Expert Judgment | Activity List
|  |  | Enterprise Environmental Factors | Decomposition | Activity Attributes
|  |  | Organizational Process Assets | Rolling Wave Planning | Milestone List
|  |  |  | Meetings | Change Requests
Project Management Plan Updates
| Planning | Sequence Activities | Project Management Plan | Precedence Diagramming Method | Project Schedule Network Diagrams
|  |  | Project Documents | Dependency Determination & Integration | Project Documents Updates
|  |  | Enterprise Environmental Factors | Leads & Lags
|  |  | Organizational Process Assets | Project Management Information System
| Planning | Estimate Activity Durations | Project Management Plan | Expert Judgment | Duration Estimates
|  |  | Project Documents | Analogous Estimating | Basis of Estimates
|  |  | Enterprise Environmental Factors | Parametric Estimating | Project Documents Updates
|  |  | Organizational Process Assets | Three-Point Estimating
Bottom-Up Estimating
Data Analysis
Decision Making
Meetings
| Planning | Develop Schedule | Project Management Plan | Schedule Network Analysis | Schedule Baseline
|  |  | Project Documents | Critical Path Method | Project Schedule
|  |  | Agreements | Resource Optimization | Schedule Data
|  |  | Enterprise Environmental Factors | Data Analysis | Project Calendars
|  |  | Organizational Process Assets | Leads & Lags | Project Management Plan Updates
|  |  |  | Schedule Compression | Project Documents Updates
Project Management Information System
Agile Release Planning
| M&C | Control Schedule | Project Management Plan | Data Analysis | Work Performance Information
|  |  | Project Documents | Critical Path Method | Schedule Forecasts
|  |  | Work Performance Data | Project Management Information System | Change Requests
|  |  | Organizational Process Assets | Resource Optimization | Project Management Plan Updates
|  |  |  | Leads & Lags | Project Documents Updates
Schedule Compression
Cost Management: | Planning | Plan Cost Management | Project Charter | Expert Judgment | Cost Management Plan
|  |  | Project Management Plan | Data Analysis
|  |  | Enterprise Environmental Factors | Meetings
Organizational Process Assets
| Planning | Estimate Costs | Project Management Plan | Expert Judgment | Cost Estimates
|  |  | Project Documents | Analogous Estimating | Basis of Estimates
|  |  | Enterprise Environmental Factors | Parametric Estimating | Project Documents Updates
|  |  | Organizational Process Assets | Bottom-Up Estimating
Three-Point Estimating
Data Analysis
Project Management Information System
Decision Making
| Planning | Determine Budget | Project Management Plan | Expert Judgment | Cost Baseline
|  |  | Project Documents | Cost Aggregation | Project Funding Requirements
|  |  | Business Documents | Data Analysis | Project Documents Updates
|  |  | Agreements | Historical Information Review
|  |  | Enterprise Environmental Factors | Funding Limit Reconciliation
|  |  | Organizational Process Assets | Financing
| M&C | Control Costs | Project Management Plan | Expert Judgment | Work Performance Information
|  |  | Project Documents | Data Analysis | Cost Forecasts
|  |  | Project Funding Requirements | To-Complete Performance Index | Change Requests
|  |  | Work Performance Data | Project Management Information System | Project Management Plan Updates
|  |  | Organizational Process Assets |  | Project Documents Updates
Quality Management: | Planning | Plan Quality Management | Project Charter | Expert Judgment | Quality Management Plan
|  |  | Project Management Plan | Data Gathering | Quality Metrics
|  |  | Project Documents | Data Analysis | Project Management Plan Updates
|  |  | Enterprise Environmental Factors | Decision Making | Project Documents Updates
|  |  | Organizational Process Assets | Data Representation
Test & Inspection Planning
Meetings
| Executing | Manage Quality | Project Management Plan | Data Gathering | Quality Reports
|  |  | Project Documents | Data Analysis | Test & Evaluation Documents
|  |  | Organizational Process Assets | Decision Making | Change Requests
|  |  |  | Data Representation | Project Management Plan Updates
|  |  |  | Audits | Project Documents Updates
Design for X
Problem Solving
Quality Improvement Methods
| M&C | Control Quality | Project Management Plan | Data Gathering | Quality Control Measurements
|  |  | Project Documents | Data Analysis | Verified Deliverables
|  |  | Approved Change Requests | Inspection | Work Performance Information
|  |  | Deliverables | Testing/Product Evaluations | Change Requests
|  |  | Work Performance Data | Data Representation | Project Management Plan Updates
|  |  | Enterprise Environmental Factors | Meetings | Project Documents Updates
Organizational Process Assets
Resource Management: | Planning | Plan Resource Management | Project Charter | Expert Judgment | Resource Management Plan
|  |  | Project Management Plan | Data Representation | Team Charter
|  |  | Project Documents | Organizational Theory | Project Documents Updates
|  |  | Enterprise Environmental Factors | Meetings
Organizational Process Assets
| Planning | Estimate Activity Resources | Project Management Plan | Expert Judgment | Resource Requirements
|  |  | Project Documents | Bottom-Up Estimating | Basis of Estimates
|  |  | Enterprise Environmental Factors | Analogous Estimating | Resource Breakdown Structure
|  |  | Organizational Process Assets | Parametric Estimating | Project Documents Updates
Data Analysis
Project Management Information System
Meetings
| Executing | Acquire Resources | Project Management Plan | Decision Making | Physical Resource Assignments
|  |  | Project Documents | Interpersonal & Team Skills | Project Team Assignments
|  |  | Enterprise Environmental Factors | Pre-Assignment | Resource Calendars
|  |  | Organizational Process Assets | Virtual Teams | Change Requests
Project Management Plan Updates
Project Documents Updates
Enterprise Environmental Factors Updates
Organizational Process Assets Updates
| Executing | Develop Team | Project Management Plan | Colocation | Team Performance Assessments
|  |  | Project Documents | Virtual Teams | Change Requests
|  |  | Enterprise Environmental Factors | Communication Technology | Project Management Plan Updates
|  |  | Organizational Process Assets | Interpersonal & Team Skills | Project Documents Updates
|  |  |  | Recognition & Rewards | Enterprise Environmental Factors Updates
|  |  |  | Training | Organizational Process Assets Updates
Individual & Team Assessments
Meetings
| Executing | Manage Team | Project Management Plan | Interpersonal & Team Skills | Change Requests
|  |  | Project Documents | Project Management Information System | Project Management Plan Updates
|  |  | Work Performance Reports |  | Project Documents Updates
|  |  | Team Performance Assessments |  | Enterprise Environmental Factors Updates
Enterprise Environmental Factors
Organizational Process Assets
| M&C | Control Resources | Project Management Plan | Data Analysis | Work Performance Information
|  |  | Project Documents | Problem Solving | Change Requests
|  |  | Work Performance Data | Interpersonal & Team Skills | Project Management Plan Updates
|  |  | Agreements | Project Management Information System | Project Documents Updates
Organizational Process Assets
Communications Management: | Planning | Plan Communications Management | Project Charter | Expert Judgment | Communications Management Plan
|  |  | Project Management Plan | Communications Requirements Analysis | Project Management Plan Updates
|  |  | Project Documents | Communication Technology | Project Documents Updates
|  |  | Enterprise Environmental Factors | Communication Models
|  |  | Organizational Process Assets | Communication Methods
Interpersonal & Team Skills
Data Representation
Meetings
| Executing | Manage Communications | Project Management Plan | Communication Technology | Project Communications
|  |  | Project Documents | Communication Methods | Project Management Plan Updates
|  |  | Work Performance Reports | Communication Skills | Project Documents Updates
|  |  | Enterprise Environmental Factors | Project Management Information System | Organizational Process Assets Updates
|  |  | Organizational Process Assets | Project Reporting
Interpersonal & Team Skills
Meetings
| M&C | Monitor Communications | Project Management Plan | Expert Judgment | Work Performance Information
|  |  | Project Documents | Project Management Information System | Change Requests
|  |  | Work Performance Data | Data Representation | Project Management Plan Updates
|  |  | Enterprise Environmental Factors | Interpersonal & Team Skills | Project Documents Updates
|  |  | Organizational Process Assets | Meetings
Risk Management: | Planning | Plan Risk Management | Project Charter | Expert Judgment | Risk Management Plan
|  |  | Project Management Plan | Data Analysis
|  |  | Project Documents | Meetings
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Identify Risks | Project Management Plan | Expert Judgment | Risk Register
|  |  | Project Documents | Data Gathering | Risk Report
|  |  | Agreements | Data Analysis | Project Documents Updates
|  |  | Procurement Documentation | Interpersonal & Team Skills
|  |  | Enterprise Environmental Factors | Prompt Lists
|  |  | Organizational Process Assets | Meetings
| Planning | Perform Qualitative Risk Analysis | Project Management Plan | Expert Judgment | Project Documents Updates
|  |  | Project Documents | Data Gathering
|  |  | Enterprise Environmental Factors | Data Analysis
|  |  | Organizational Process Assets | Interpersonal & Team Skills
Risk Categorization
Data Representation
Meetings
| Planning | Perform Quantitative Risk Analysis | Project Management Plan | Expert Judgment | Project Documents Updates
|  |  | Project Documents | Data Gathering
|  |  | Enterprise Environmental Factors | Interpersonal & Team Skills
|  |  | Organizational Process Assets | Representations of Uncertainty
Data Analysis
| Planning | Plan Risk Responses | Project Management Plan | Expert Judgment | Change Requests
|  |  | Project Documents | Data Gathering | Project Management Plan Updates
|  |  | Enterprise Environmental Factors | Interpersonal & Team Skills | Project Documents Updates
|  |  | Organizational Process Assets | Strategies for Threats
Strategies for Opportunities
Contingent Response Strategies
Strategies for Overall Project Risk
Data Analysis
Decision Making
| Executing | Implement Risk Responses | Project Management Plan | Expert Judgment | Change Requests
|  |  | Project Documents | Interpersonal & Team Skills | Project Documents Updates
|  |  | Organizational Process Assets | Project Management Information System
| M&C | Monitor Risks | Project Management Plan | Data Analysis | Work Performance Information
|  |  | Project Documents | Audits | Change Requests
|  |  | Work Performance Data | Meetings | Project Management Plan Updates
|  |  | Work Performance Reports |  | Project Documents Updates
Organizational Process Assets Updates
Procurement Management: | Planning | Plan Procurement Management | Project Charter | Expert Judgment | Procurement Management Plan
|  |  | Business Documents | Data Gathering | Procurement Strategy
|  |  | Project Management Plan | Data Analysis | Bid Documents
|  |  | Project Documents | Source Selection Analysis | Procurement Statement of Work
|  |  | Enterprise Environmental Factors | Meetings | Source Selection Criteria
|  |  | Organizational Process Assets |  | Make-or-Buy Decisions
Independent Cost Estimates
Change Requests
Project Documents Updates
Organizational Process Assets Updates
| Executing | Conduct Procurements | Project Management Plan | Expert Judgment | Selected Sellers
|  |  | Project Documents | Advertising | Agreements
|  |  | Procurement Documentation | Bidder Conferences | Change Requests
|  |  | Seller Proposals | Data Analysis | Project Management Plan Updates
|  |  | Enterprise Environmental Factors | Interpersonal & Team Skills | Project Documents Updates
|  |  | Organizational Process Assets |  | Organizational Process Assets Updates
| M&C | Control Procurements | Project Management Plan | Expert Judgment | Closed Procurements
|  |  | Project Documents | Claims Administration | Work Performance Information
|  |  | Agreements | Data Analysis | Procurement Documentation Updates
|  |  | Procurement Documentation | Inspection | Change Requests
|  |  | Approved Change Requests | Audits | Project Management Plan Updates
|  |  | Work Performance Data |  | Project Documents Updates
|  |  | Enterprise Environmental Factors |  | Organizational Process Assets Updates
Organizational Process Assets
Stakeholder Management | Initiating | Identify Stakeholders | Project Charter | Expert Judgment | Stakeholder Register
|  |  | Business Documents | Data Gathering | Change Requests
|  |  | Project Management Plan | Data Analysis | Project Management Plan Updates
|  |  | Project Documents | Data Representation | Project Documents Updates
|  |  | Agreements | Meetings
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Plan Stakeholder Engagement | Project Charter | Expert Judgment | Stakeholder Engagement Plan
|  |  | Project Management Plan | Data Gathering
|  |  | Project Documents | Data Analysis
|  |  | Agreements | Decision Making
|  |  | Enterprise Environmental Factors | Data Representation
|  |  | Organizational Process Assets | Meetings
| Executing | Manage Stakeholder Engagement | Project Management Plan | Expert Judgment | Change Requests
|  |  | Project Documents | Communication Skills | Project Management Plan Updates
|  |  | Enterprise Environmental Factors | Interpersonal & Team Skills | Project Documents Updates
|  |  | Organizational Process Assets | Ground Rules
Meetings
| M&C | Monitor Stakeholder Engagement | Project Management Plan | Data Analysis | Work Performance Information
|  |  | Project Documents | Decision Making | Change Requests
|  |  | Work Performance Data | Data Representation | Project Management Plan Updates
|  |  | Enterprise Environmental Factors | Communication Skills | Project Documents Updates
|  |  | Organizational Process Assets | Interpersonal & Team Skills
Meetings

## Detailed View
ITTOs - Detailed View |  |  |  |  | projectprep.org
Knowledge Area | Process Group | Process | Inputs | Tools & Techniques | Outputs
Integration Management: | Initiating | Develop Project Charter | Business Documents | Expert Judgment | Project Charter
|  |  | - Business Case | Data Gathering | Assumption Log
|  |  | - Benefits Management Plan | - Brainstorming
|  |  | Agreements | - Focus Groups
|  |  | Enterprise Environmental Factors | - Interviews
|  |  | Organizational Process Assets | Interpersonal & Team Skills
- Conflict Management
- Facilitation
- Meeting Management
Meetings
| Planning | Develop Project Management Plan | Project Charter | Expert Judgment | Project Management Plan
|  |  | Outputs from Other Processes | Data Gathering
|  |  | Enterprise Environmental Factors | - Brainstorming
|  |  | Organizational Process Assets | - Checklists
- Focus Groups
- Interviews
Interpersonal & Team Skills
- Conflict Management
- Facilitation
- Meeting Management
Meetings
| Executing | Direct and Manage Project Work | Project Management Plan | Expert Judgment | Deliverables
|  |  | - Any Component | Project Management Information System | Work Performance Data
|  |  | Project Documents | Meetings | Issue Log
|  |  | - Change Log |  | Change Requests
|  |  | - Lessons Learned Register |  | Project Management Plan Updates
|  |  | - Milestone List |  | - Any Component
|  |  | - Project Communications |  | Project Documents Updates
|  |  | - Project Schedule |  | - Activity List
|  |  | - Requirements Traceability Matrix |  | - Assumption Log
|  |  | - Risk Register |  | - Lessons Learned Register
|  |  | - Risk Report |  | - Requirements Documentation
|  |  | Approved Change Requests |  | - Risk Register
|  |  | Enterprise Environmental Factors |  | - Stakeholder Register
|  |  | Organizational Process Assets |  | Organizational Process Assets Updates
| Executing | Manage Project Knowledge | Project Management Plan | Expert Judgment | Lessons Learned Register
|  |  | - All Components | Knowledge Management | Project Management Plan Updates
|  |  | Project Documents | Information Management | - Any Component
|  |  | - Lessons Learned Register | Interpersonal & Team Skills | Organizational Process Assets Updates
|  |  | - Project Team Assignments | - Active Listening
|  |  | - Resource Breakdown Structure | - Facilitation
|  |  | - Source Selection Criteria | - Leadership
|  |  | - Stakeholder Register | - Networking
|  |  | Deliverables | - Political Awareness
Enterprise Environmental Factors
Organizational Process Assets
| M&C | Monitor and Control Project Work | Project Management Plan | Expert Judgment | Work Performance Reports
|  |  | - Any Component | Data Analysis | Change Requests
|  |  | Project Documents | - Alternatives Analysis | Project Management Plan Updates
|  |  | - Assumption Log | - Cost-Benefit Analysis | - Any Component
|  |  | - Basis of Estimates | - Earned Value Analysis | Project Documents Updates
|  |  | - Cost Forecasts | - Root Cause Analysis | - Cost Forecasts
|  |  | - Issue Log | - Trend Analysis | - Issue Log
|  |  | - Lessons Learned Register | - Variance Analysis | - Lessons Learned Register
|  |  | - Milestone List | Decision Making | - Risk Register
|  |  | - Quality Reports | Meetings | - Schedule Forecasts
- Risk Register
- Risk Report
- Schedule Forecasts
Work Performance Information
Agreements
Enterprise Environmental Factors
Organizational Process Assets
| M&C | Perform Integrated Change Control | Project Management Plan | Expert Judgment | Approved Change Requests
|  |  | - Change Management Plan | Change Control Tools | Project Management Plan Updates
|  |  | - Configuration Management Plan | Data Analysis | - Any Component
|  |  | - Scope Baseline | - Alternatives Analysis | Project Documents Updates
|  |  | - Schedule Baseline | - Cost-Benefit Analysis | - Change Log
|  |  | - Cost Baseline | Decision Making
|  |  | Project Documents | - Voting
|  |  | - Basis of Estimates | - Autocratic Decision Making
|  |  | - Requirements Traceability Matrix | - Multi-Criteria Decision Analysis
|  |  | - Risk Report | Meetings
Work Performance Reports
Change Requests
Enterprise Environmental Factors
Organizational Process Assets
| Closing | Close Project or Phase | Project Charter | Expert Judgment | Project Documents Updates
|  |  | Project Management Plan | Data Analysis | - Lessons Learned Register
|  |  | - All Components | - Document Analysis | Final Product, Service, Or Result Transition
|  |  | Project Documents | - Regression Analysis | Final Report
|  |  | - Assumption Log | - Trend Analysis | Organizational Process Assets Updates
|  |  | - Basis of Estimates | - Variance Analysis
|  |  | - Change Log | Meetings
- Issue Log
- Lessons Learned Register
- Milestone List
- Project Communications
- Quality Control Measurements
- Quality Reports
- Requirements Documentation
- Risk Register
- Risk Report
Accepted Deliverables
Business Documents
- Business Case
- Benefits Management Plan
Agreements
Procurement Documentation
Organizational Process Assets
Scope Management: | Planning | Plan Scope Management | Project Charter | Expert Judgment | Scope Management Plan
|  |  | Project Management Plan | Data Analysis | Requirements Management Plan
|  |  | - Quality Management Plan | - Alternatives Analysis
|  |  | - Project Life Cycle Description | Meetings
- Development Approach
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Collect Requirements | Project Charter | Expert Judgment | Requirements Documentation
|  |  | Project Management Plan | Data Gathering | Requirements Traceability Matrix
|  |  | - Scope Management Plan | - Brainstorming
|  |  | - Requirements Management Plan | - Interviews
|  |  | - Stakeholder Engagement Plan | - Focus Groups
|  |  | Project Documents | - Questionnaires & Surveys
|  |  | - Assumption Log | - Benchmarking
|  |  | - Lessons Learned Register | Data Analysis
|  |  | - Stakeholder Register | - Document Analysis
|  |  | Business Documents | Decision Making
|  |  | - Business Case | - Voting
|  |  | Agreements | - Multi-Criteria Decision Analysis
|  |  | Enterprise Environmental Factors | Data Representation
|  |  | Organizational Process Assets | - Affinity Diagrams
- Mind Mapping
Interpersonal & Team Skills
- Nominal Group Technique
- Observation/Conversation
- Facilitation
Context Diagram
Prototypes
| Planning | Define Scope | Project Charter | Expert Judgment | Project Scope Statement
|  |  | Project Management Plan | Data Analysis | Project Documents Updates
|  |  | - Scope Management Plan | - Alternatives Analysis | - Assumption Log
|  |  | Project Documents | Decision Making | - Requirements Documentation
|  |  | - Assumption Log | - Multi-Criteria Decision Analysis | - Requirements Traceability Matrix
|  |  | - Requirements Documentation | Interpersonal & Team Skills | - Stakeholder Register
|  |  | - Risk Register | - Facilitation
|  |  | Enterprise Environmental Factors | Product Analysis
Organizational Process Assets
| Planning | Create WBS | Project Management Plan | Expert Judgment | Scope Baseline
|  |  | - Scope Management Plan | Decomposition | Project Documents Updates
|  |  | Project Documents |  | - Assumption Log
|  |  | - Project Scope Statement |  | - Requirements Documentation
- Requirements Documentation
Enterprise Environmental Factors
Organizational Process Assets
| M&C | Validate Scope | Project Management Plan | Inspection | Accepted Deliverables
|  |  | - Scope Management Plan | Decision Making | Work Performance Information
|  |  | - Requirements Management Plan | - Voting | Change Requests
|  |  | - Scope Baseline |  | Project Documents Updates
|  |  | Project Documents |  | - Lessons Learned Register
|  |  | - Lessons Learned Register |  | - Requirements Documentation
|  |  | - Quality Reports |  | - Requirements Traceability Matrix
- Requirements Documentation
- Requirements Traceability Matrix
Verified Deliverables
Work Performance Data
| M&C | Control Scope | Project Management Plan | Data Analysis | Work Performance Information
|  |  | - Scope Management Plan | - Variance Analysis | Change Requests
|  |  | - Requirements Management Plan | - Trend Analysis | Project Management Plan Updates
|  |  | - Change Management Plan |  | - Scope Management Plan
|  |  | - Configuration Management Plan |  | - Scope Baseline
|  |  | - Scope Baseline |  | - Schedule Baseline
|  |  | - Performance Measurement Baseline |  | - Cost Baseline
|  |  | Project Documents |  | - Performance Measurement Baseline
|  |  | - Lessons Learned Register |  | Project Documents Updates
|  |  | - Requirements Documentation |  | - Lessons Learned Register
|  |  | - Requirements Traceability Matrix |  | - Requirements Documentation
|  |  | Work Performance Data |  | - Requirements Traceability Matrix
Organizational Process Assets
Schedule Management: | Planning | Plan Schedule Management | Project Charter | Expert Judgment | Schedule Management Plan
|  |  | Project Management Plan | Data Analysis
|  |  | - Scope Management Plan | Meetings
- Development Approach
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Define Activities | Project Management Plan | Expert Judgment | Activity List
|  |  | - Schedule Management Plan | Decomposition | Activity Attributes
|  |  | - Scope Baseline | Rolling Wave Planning | Milestone List
|  |  | Enterprise Environmental Factors | Meetings | Change Requests
|  |  | Organizational Process Assets |  | Project Management Plan Updates
- Schedule Baseline
- Cost Baseline
| Planning | Sequence Activities | Project Management Plan | Precedence Diagramming Method | Project Schedule Network Diagrams
|  |  | - Schedule Management Plan | Dependency Determination & Integration | Project Documents Updates
|  |  | - Scope Baseline | Leads & Lags | - Activity Attributes
|  |  | Project Documents | Project Management Information System | - Activity List
|  |  | - Activity Attributes |  | - Assumption Log
|  |  | - Activity List |  | - Milestone List
- Assumption Log
- Milestone List
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Estimate Activity Durations | Project Management Plan | Expert Judgment | Duration Estimates
|  |  | - Schedule Management Plan | Analogous Estimating | Basis of Estimates
|  |  | - Scope Baseline | Parametric Estimating | Project Documents Updates
|  |  | Project Documents | Three-Point Estimating | - Activity Attributes
|  |  | - Activity Attributes | Bottom-Up Estimating | - Assumption Log
|  |  | - Activity List | Data Analysis | - Lessons Learned Register
|  |  | - Assumption Log | - Alternatives Analysis
|  |  | - Lessons Learned Register | - Reserve Analysis
|  |  | - Milestone List | Decision Making
|  |  | - Project Team Assignments | Meetings
- Resource Breakdown Structure
- Resource Calendars
- Resource Requirements
- Risk Register
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Develop Schedule | Project Management Plan | Schedule Network Analysis | Schedule Baseline
|  |  | - Schedule Management Plan | Critical Path Method | Project Schedule
|  |  | - Scope Baseline | Resource Optimization | Schedule Data
|  |  | Project Documents | Data Analysis | Project Calendars
|  |  | - Activity Attributes | - What-If Scenario Analysis | Change Requests
|  |  | - Activity List | - Simulation | Project Management Plan Updates
|  |  | - Assumption Log | Leads & Lags | - Schedule Management Plan
|  |  | - Basis of Estimates | Schedule Compression | - Cost Baseline
|  |  | - Duration Estimates | Project Management Information System | Project Documents Updates
|  |  | - Lessons Learned Register | Agile Release Planning | - Activity Attributes
|  |  | - Milestone List |  | - Assumption Log
|  |  | - Project Schedule Network Diagrams |  | - Duration Estimates
|  |  | - Project Team Assignments |  | - Lessons Learned Register
|  |  | - Resource Calendars |  | - Resource Requirements
|  |  | - Resource Requirements |  | - Risk Register
- Risk Register
Agreements
Enterprise Environmental Factors
Organizational Process Assets
| M&C | Control Schedule | Project Management Plan | Data Analysis | Work Performance Information
|  |  | - Schedule Management Plan | - Earned Value Analysis | Schedule Forecasts
|  |  | - Schedule Baseline | - Iteration Burndown Chart | Change Requests
|  |  | - Scope Baseline | - Performance Reviews | Project Management Plan Updates
|  |  | - Performance Measurement Baseline | - Trend Analysis | - Schedule Management Plan
|  |  | Project Documents | - Variance Analysis | - Schedule Baseline
|  |  | - Lessons Learned Register | - What-If Scenario Analysis | - Cost Baseline
|  |  | - Project Calendars | Critical Path Method | - Performance Measurement Baseline
|  |  | - Project Schedule | Project Management Information System | Project Documents Updates
|  |  | - Resource Calendars | Resource Optimization | - Assumption Log
|  |  | - Schedule Data | Leads & Lags | - Basis of Estimates
|  |  | Work Performance Data | Schedule Compression | - Lessons Learned Register
|  |  | Organizational Process Assets |  | - Project Schedule
- Resource Calendars
- Risk Register
- Schedule Data
Cost Management: | Planning | Plan Cost Management | Project Charter | Expert Judgment | Cost Management Plan
|  |  | Project Management Plan | Data Analysis
|  |  | - Schedule Management Plan | Meetings
- Risk Management Plan
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Estimate Costs | Project Management Plan | Expert Judgment | Cost Estimates
|  |  | - Cost Management Plan | Analogous Estimating | Basis of Estimates
|  |  | - Quality Management Plan | Parametric Estimating | Project Documents Updates
|  |  | - Scope Baseline | Bottom-Up Estimating | - Assumption Log
|  |  | Project Documents | Three-Point Estimating | - Lessons Learned Register
|  |  | - Lessons Learned Register | Data Analysis | - Risk Register
|  |  | - Project Schedule | - Alternatives Analysis
|  |  | - Resources Requirements | - Reserve Analysis
|  |  | - Risk Register | - Cost of Quality
|  |  | Enterprise Environmental Factors | Project Management Information System
|  |  | Organizational Process Assets | Decision Making
- Voting
| Planning | Determine Budget | Project Management Plan | Expert Judgment | Cost Baseline
|  |  | - Cost Management Plan | Cost Aggregation | Project Funding Requirements
|  |  | - Resource Management Plan | Data Analysis | Project Documents Updates
|  |  | - Scope Baseline | - Reserve Analysis | - Cost Estimates
|  |  | Project Documents | Historical Information Review | - Project Schedule
|  |  | - Basis of Estimates | Funding Limit Reconciliation | - Risk Register
|  |  | - Cost Estimates | Financing
- Project Schedule
- Risk Register
Business Documents
- Business Case
- Benefits Management Plan
Agreements
Enterprise Environmental Factors
Organizational Process Assets
| M&C | Control Costs | Project Management Plan | Expert Judgment | Work Performance Information
|  |  | - Cost Management Plan | Data Analysis | Cost Forecasts
|  |  | - Cost Baseline | - Earned Value Analysis | Change Requests
|  |  | - Performance Measurement Baseline | - Variance Analysis | Project Management Plan Updates
|  |  | Project Documents | - Trend Analysis | - Cost Management Plan
|  |  | - Lessons Learned Register | - Reserve Analysis | - Cost Baseline
|  |  | Project Funding Requirements | To-Complete Performance Index | - Performance Measurement Baseline
|  |  | Work Performance Data | Project Management Information System | Project Documents Updates
|  |  | Organizational Process Assets |  | - Assumption Log
- Basis of Estimates
- Cost Estimates
- Lessons Learned Register
- Risk Register
Quality Management: | Planning | Plan Quality Management | Project Charter | Expert Judgment | Quality Management Plan
|  |  | Project Management Plan | Data Gathering | Quality Metrics
|  |  | - Requirements Management Plan | - Benchmarking | Project Management Plan Updates
|  |  | - Risk Management Plan | - Brainstorming | - Risk Management Plan
|  |  | - Stakeholder Engagement Plan | - Interviews | - Scope Baseline
|  |  | - Scope Baseline | Data Analysis | Project Documents Updates
|  |  | Project Documents | - Cost-Benefit Analysis | - Lessons Learned Register
|  |  | - Assumption Log | - Cost of Quality | - Requirements Traceability Matrix
|  |  | - Requirements Documentation | Decision Making | - Risk Register
|  |  | - Requirements Traceability Matrix | - Multi-Criteria Decision Analysis | - Stakeholder Register
|  |  | - Risk Register | Data Representation
|  |  | - Stakeholder Register | - Flowcharts
|  |  | Enterprise Environmental Factors | - Logical Data Model
|  |  | Organizational Process Assets | - Matrix Diagrams
- Mind Mapping
Test & Inspection Planning
Meetings
| Executing | Manage Quality | Project Management Plan | Data Gathering | Quality Reports
|  |  | - Quality Management Plan | - Checklists | Test & Evaluation Documents
|  |  | Project Documents | Data Analysis | Change Requests
|  |  | - Lessons Learned Register | - Alternatives Analysis | Project Management Plan Updates
|  |  | - Quality Control Measurements | - Document Analysis | - Quality Management Plan
|  |  | - Quality Metrics | - Process Analysis | - Scope Baseline
|  |  | - Risk Report | - Root Cause Analysis | - Schedule Baseline
|  |  | Organizational Process Assets | Decision Making | - Cost Baseline
|  |  |  | - Multi-Criteria Decision Analysis | Project Documents Updates
|  |  |  | Data Representation | - Issue Log
|  |  |  | - Affinity Diagrams | - Lessons Learned Register
|  |  |  | - Cause-and-Effect Diagrams | - Risk Register
- Flowcharts
- Histograms
- Matrix Diagrams
- Scatter Diagrams
Audits
Design for X
Problem Solving
Quality Improvement Methods
| M&C | Control Quality | Project Management Plan | Data Gathering | Quality Control Measurements
|  |  | - Quality Management Plan | - Checklists | Verified Deliverables
|  |  | Project Documents | - Check Sheets | Work Performance Information
|  |  | - Lessons Learned Register | - Statistical Sampling | Change Requests
|  |  | - Quality Metrics | - Questionnaires & Surveys | Project Management Plan Updates
|  |  | - Test & Evaluation Documents | Data Analysis | - Quality Management Plan
|  |  | Approved Change Requests | - Performance Reviews | Project Documents Updates
|  |  | Deliverables | - Root Cause Analysis | - Issue Log
|  |  | Work Performance Data | Inspection | - Lessons Learned Register
|  |  | Enterprise Environmental Factors | Testing/Product Evaluations | - Risk Register
|  |  | Organizational Process Assets | Data Representation | - Test & Evaluation Documents
- Cause-and-Effect Diagrams
- Control Charts
- Histograms
- Scatter Diagrams
Meetings
Resource Management: | Planning | Plan Resource Management | Project Charter | Expert Judgment | Resource Management Plan
|  |  | Project Management Plan | Data Representation | Team Charter
|  |  | - Quality Management Plan | - Hierarchical Charts | Project Documents Updates
|  |  | - Scope Baseline | - Responsibility Matrix | - Assumption Log
|  |  | Project Documents | - Text-Oriented Formats | - Risk Register
|  |  | - Project Schedule | Organizational Theory
|  |  | - Requirements Documentation | Meetings
- Risk Register
- Stakeholder Register
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Estimate Activity Resources | Project Management Plan | Expert Judgment | Resource Requirements
|  |  | - Resource Management Plan | Bottom-Up Estimating | Basis of Estimates
|  |  | - Scope Baseline | Analogous Estimating | Resource Breakdown Structure
|  |  | Project Documents | Parametric Estimating | Project Documents Updates
|  |  | - Activity Attributes | Data Analysis | - Activity Attributes
|  |  | - Activity List | - Alternatives Analysis | - Assumption Log
|  |  | - Assumption Log | Project Management Information System | - Lessons Learned Register
|  |  | - Cost Estimates | Meetings
- Resource Calendars
- Risk Register
Enterprise Environmental Factors
Organizational Process Assets
| Executing | Acquire Resources | Project Management Plan | Decision Making | Physical Resource Assignments
|  |  | - Resource Management Plan | - Multi-Criteria Decision Analysis | Project Team Assignments
|  |  | - Procurement Management Plan | Interpersonal & Team Skills | Resource Calendars
|  |  | - Cost Baseline | - Negotiation | Change Requests
|  |  | Project Documents | Pre-Assignment | Project Management Plan Updates
|  |  | - Project Schedule | Virtual Teams | - Resource Management Plan
|  |  | - Resource Calendars |  | - Cost Baseline
|  |  | - Resource Requirements |  | Project Documents Updates
|  |  | - Stakeholder Register |  | - Lessons Learned Register
|  |  | Enterprise Environmental Factors |  | - Project Schedule
|  |  | Organizational Process Assets |  | - Resource Breakdown Structure
- Resource Requirements
- Risk Register
- Stakeholder Register
Enterprise Environmental Factors Updates
Organizational Process Assets Updates
| Executing | Develop Team | Project Management Plan | Colocation | Team Performance Assessments
|  |  | - Resource Management Plan | Virtual Teams | Change Requests
|  |  | Project Documents | Communication Technology | Project Management Plan Updates
|  |  | - Lessons Learned Register | Interpersonal & Team Skills | - Resource Management Plan
|  |  | - Project Schedule | - Conflict Management | Project Documents Updates
|  |  | - Project Team Assignments | - Influencing | - Lessons Learned Register
|  |  | - Resource Calendars | - Motivation | - Project Schedule
|  |  | - Team Charter | - Negotiation | - Project Team Assignments
|  |  | Enterprise Environmental Factors | - Team Building | - Resource Calendars
|  |  | Organizational Process Assets | Recognition & Rewards | - Team Charter
|  |  |  | Training | Enterprise Environmental Factors Updates
|  |  |  | Individual & Team Assessments | Organizational Process Assets Updates
Meetings
| Executing | Manage Team | Project Management Plan | Interpersonal & Team Skills | Change Requests
|  |  | - Resource Management Plan | - Conflict Management | Project Management Plan Updates
|  |  | Project Documents | - Decision Making | - Resource Management Plan
|  |  | - Issue Log | - Emotional Intelligence | - Schedule Baseline
|  |  | - Lessons Learned Register | - Influencing | - Cost Baseline
|  |  | - Project Team Assignments | - Leadership | Project Documents Updates
|  |  | - Team Charter | Project Management Information System | - Issue Log
|  |  | Work Performance Reports |  | - Lessons Learned Register
|  |  | Team Performance Assessments |  | - Project Team Assignments
|  |  | Enterprise Environmental Factors |  | Enterprise Environmental Factors Updates
Organizational Process Assets
| M&C | Control Resources | Project Management Plan | Data Analysis | Work Performance Information
|  |  | - Resource Management Plan | - Alternatives Analysis | Change Requests
|  |  | Project Documents | - Cost-Benefit Analysis | Project Management Plan Updates
|  |  | - Issue Log | - Performance Reviews | - Resource Management Plan
|  |  | - Lessons Learned Register | - Trend Analysis | - Schedule Baseline
|  |  | - Physical Resource Assignments | Problem Solving | - Cost Baseline
|  |  | - Project Schedule | Interpersonal & Team Skills | Project Documents Updates
|  |  | - Resource Breakdown Structure | - Negotiation | - Assumption Log
|  |  | - Resource Requirements | - Influencing | - Issue Log
|  |  | - Risk Register | Project Management Information System | - Lessons Learned Register
|  |  | Work Performance Data |  | - Physical Resource Assignments
|  |  | Agreements |  | - Resource Breakdown Structure
|  |  | Organizational Process Assets |  | - Risk Register
Communications Management: | Planning | Plan Communications Management | Project Charter | Expert Judgment | Communications Management Plan
|  |  | Project Management Plan | Communications Requirements Analysis | Project Management Plan Updates
|  |  | - Resource Management Plan | Communication Technology | - Stakeholder Engagement Plan
|  |  | - Stakeholder Engagement Plan | Communication Models | Project Documents Updates
|  |  | Project Documents | Communication Methods | - Project Schedule
|  |  | - Requirements Documentation | Interpersonal & Team Skills | - Stakeholder Register
|  |  | - Stakeholder Register | - Communication Styles Assessment
|  |  | Enterprise Environmental Factors | - Political Awareness
|  |  | Organizational Process Assets | - Cultural Awareness
Data Representation
- Stakeholder Engagement Assessment Matrix
Meetings
| Executing | Manage Communications | Project Management Plan | Communication Technology | Project Communications
|  |  | - Resource Management Plan | Communication Methods | Project Management Plan Updates
|  |  | - Communications Management Plan | Communication Skills | - Communications Management Plan
|  |  | - Stakeholder Engagement Plan | - Communication Competence | - Stakeholder Engagement Plan
|  |  | Project Documents | - Feedback | Project Documents Updates
|  |  | - Change Log | - Nonverbal | - Issue Log
|  |  | - Issue Log | - Presentations | - Lessons Learned Register
|  |  | - Lessons Learned Register | Project Management Information System | - Project Schedule
|  |  | - Quality Report | Project Reporting | - Risk Register
|  |  | - Risk Report | Interpersonal & Team Skills | - Stakeholder Register
|  |  | - Stakeholder Register | - Active Listening | Organizational Process Assets Updates
|  |  | Work Performance Reports | - Conflict Management
|  |  | Enterprise Environmental Factors | - Cultural Awareness
|  |  | Organizational Process Assets | - Meeting Management
- Networking
- Political Awareness
Meetings
| M&C | Monitor Communications | Project Management Plan | Expert Judgment | Work Performance Information
|  |  | - Resource Management Plan | Project Management Information System | Change Requests
|  |  | - Communications Management Plan | Data Analysis | Project Management Plan Updates
|  |  | - Stakeholder Engagement Plan | - Stakeholder Engagement Assessment Matrix | - Communications Management Plan
|  |  | Project Documents | Interpersonal & Team Skills | - Stakeholder Engagement Plan
|  |  | - Issue Log | - Observation/Conversation | Project Documents Updates
|  |  | - Lessons Learned Register | Meetings | - Issue Log
|  |  | - Project Communications |  | - Lessons Learned Register
|  |  | Work Performance Data |  | - Stakeholder Register
Enterprise Environmental Factors
Organizational Process Assets
Risk Management: | Planning | Plan Risk Management | Project Charter | Expert Judgment | Risk Management Plan
|  |  | Project Management Plan | Data Analysis
|  |  | - All Components | - Stakeholder Analysis
|  |  | Project Documents | Meetings
- Stakeholder Register
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Identify Risks | Project Management Plan | Expert Judgment | Risk Register
|  |  | - Requirements Management Plan | Data Gathering | Risk Report
|  |  | - Schedule Management Plan | - Brainstorming | Project Documents Updates
|  |  | - Cost Management Plan | - Checklists | - Assumption Log
|  |  | - Quality Management Plan | - Interviews | - Issue Log
|  |  | - Resource Management Plan | Data Analysis | - Lessons Learned Register
|  |  | - Risk Management Plan | - Root Cause Analysis
|  |  | - Scope Baseline | - Assumption & Constraint Analysis
|  |  | - Schedule Baseline | - SWOT Analysis
|  |  | - Cost Baseline | - Documents Analysis
|  |  | Project Documents | Interpersonal & Team Skills
|  |  | - Assumption Log | - Facilitation
|  |  | - Cost Estimates | Prompt Lists
|  |  | - Duration Estimates | Meetings
- Issue Log
- Lessons Learned Register
- Requirements Documentation
- Resource Requirements
- Stakeholder Register
Agreements
Procurement Documentation
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Perform Qualitative Risk Analysis | Project Management Plan | Expert Judgment | Project Documents Updates
|  |  | - Risk Management Plan | Data Gathering | - Assumption Log
|  |  | Project Documents | - Interviews | - Issue Log
|  |  | - Assumption Log | Data Analysis | - Risk Register
|  |  | - Risk Register | - Risk Data Quality Assessment | - Risk Report
|  |  | - Stakeholder Register | - Risk Probability & Impact Assessment
|  |  | Enterprise Environmental Factors | - Assessment of Other Risk Parameters
|  |  | Organizational Process Assets | Interpersonal & Team Skills
- Facilitation
Risk Categorization
Data Representation
- Probability & Impact Matrix
- Hierarchical Charts
Meetings
| Planning | Perform Quantitative Risk Analysis | Project Management Plan | Expert Judgment | Project Documents Updates
|  |  | - Risk Management Plan | Data Gathering | - Risk Report
|  |  | - Scope Baseline | - Interviews
|  |  | - Schedule Baseline | Interpersonal & Team Skills
|  |  | - Cost Baseline | - Facilitation
|  |  | Project Documents | Representation of Uncertainty
|  |  | - Assumption Log | Data Analysis
|  |  | - Basis of Estimates | - Simulations
|  |  | - Cost Estimates | - Sensitivity Analysis
|  |  | - Cost Forecasts | - Decision Tree Analysis
|  |  | - Duration Estimates | - Influence Diagrams
- Milestone List
- Resource Requirements
- Risk Register
- Risk Report
- Schedule Forecasts
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Plan Risk Responses | Project Management Plan | Expert Judgment | Change Requests
|  |  | - Resource Management Plan | Data Gathering | Project Management Plan Updates
|  |  | - Risk Management Plan | - Interviews | - Schedule Management Plan
|  |  | - Cost Baseline | Interpersonal & Team Skills | - Cost Management Plan
|  |  | Project Documents | - Facilitation | - Quality Management Plan
|  |  | - Lessons Learned Register | Strategies for Threats | - Resource Management Plan
|  |  | - Project Schedule | Strategies for Opportunities | - Procurement Management Plan
|  |  | - Project Team Assignments | Contingent Response Strategies | - Scope Baseline
|  |  | - Resource Calendars | Strategies for Overall Project Risk | - Schedule Baseline
|  |  | - Risk Register | Data Analysis | - Cost Baseline
|  |  | - Risk Report | - Alternatives Analysis | Project Documents Updates
|  |  | - Stakeholder Register | - Cost-Benefit Analysis | - Assumption Log
|  |  | Enterprise Environmental Factors | Decision Making | - Cost Forecasts
|  |  | Organizational Process Assets | - Multi-Criteria Decision Analysis | - Lessons Learned Register
- Project Schedule
- Project Team Assignments
- Risk Register
- Risk Report
| Executing | Implement Risk Responses | Project Management Plan | Expert Judgment | Change Requests
|  |  | - Risk Management Plan | Interpersonal & Team Skills | Project Documents Updates
|  |  | Project Documents | - Influencing | - Issue Log
|  |  | - Lessons Learned Register | Project Management Information System | - Lessons Learned Register
|  |  | - Risk Register |  | - Project Team Assignments
|  |  | - Risk Report |  | - Risk Register
|  |  | Organizational Process Assets |  | - Risk Report
| M&C | Monitor Risks | Project Management Plan | Data Analysis | Work Performance Information
|  |  | - Risk Management Plan | - Technical Performance Analysis | Change Requests
|  |  | Project Documents | - Reserve Analysis | Project Management Plan Updates
|  |  | - Issue Log | Audits | - Any Component
|  |  | - Lessons Learned Register | Meetings | Project Documents Updates
|  |  | - Risk Register |  | - Assumption Log
|  |  | - Risk Report |  | - Issue Log
|  |  | Work Performance Data |  | - Lessons Learned Register
|  |  | Work Performance Reports |  | - Risk Register
- Risk Report
Organizational Process Assets Updates
Procurement Management: | Planning | Plan Procurement Management | Project Charter | Expert Judgment | Procurement Management Plan
|  |  | Business Documents | Data Gathering | Procurement Strategy
|  |  | - Business Case | - Market Research | Bid Documents
|  |  | - Benefits Management Plan | Data Analysis | Procurement Statement of Work
|  |  | Project Management Plan | - Make-Or-Buy Analysis | Source Selection Criteria
|  |  | - Scope Management Plan | Source Selection Analysis | Make-Or-Buy Decisions
|  |  | - Quality Management Plan | Meetings | Independent Cost Estimates
|  |  | - Resource Management Plan |  | Change Requests
|  |  | - Scope Baseline |  | Project Documents Updates
|  |  | Project Documents |  | - Lessons Learned Register
|  |  | - Milestone List |  | - Milestone List
|  |  | - Project Team Assignments |  | - Requirements Documentation
|  |  | - Requirements Documentation |  | - Requirements Traceability Matrix
|  |  | - Requirements Traceability Matrix |  | - Risk Register
|  |  | - Resource Requirements |  | - Stakeholder Register
|  |  | - Risk Register |  | Organizational Process Assets Updates
- Stakeholder Register
Enterprise Environmental Factors
Organizational Process Assets
| Executing | Conduct Procurements | Project Management Plan | Expert Judgment | Selected Sellers
|  |  | - Scope Management Plan | Advertising | Agreements
|  |  | - Requirements Management Plan | Bidder Conferences | Change Requests
|  |  | - Communications Management Plan | Data Analysis | Project Management Plan Updates
|  |  | - Risk Management Plan | - Proposal Evaluation | - Requirements Management Plan
|  |  | - Procurement Management Plan | Interpersonal & Team Skills | - Quality Management Plan
|  |  | - Configuration Management Plan | - Negotiation | - Communications Management Plan
|  |  | - Cost Baseline |  | - Risk Management Plan
|  |  | Project Documents |  | - Procurement Management Plan
|  |  | - Lessons Learned Register |  | - Scope Baseline
|  |  | - Project Schedule |  | - Schedule Baseline
|  |  | - Requirements Documentation |  | - Cost Baseline
|  |  | - Risk Register |  | Project Documents Updates
|  |  | - Stakeholder Register |  | - Lessons Learned Register
|  |  | Procurement Documentation |  | - Requirements Documentation
|  |  | Seller Proposals |  | - Requirements Traceability Matrix
|  |  | Enterprise Environmental Factors |  | - Resource Calendars
|  |  | Organizational Process Assets |  | - Risk Register
- Stakeholder Register
Organizational Process Assets Updates
| M&C | Control Procurements | Project Management Plan | Expert Judgment | Closed Procurements
|  |  | - Requirements Management Plan | Claims Administration | Work Performance Information
|  |  | - Risk Management Plan | Data Analysis | Procurement Documentation Updates
|  |  | - Procurement Management Plan | - Performance Reviews | Change Requests
|  |  | - Change Management Plan | - Earned Value Analysis | Project Management Plan Updates
|  |  | - Schedule Baseline | - Trend Analysis | - Risk Management Plan
|  |  | Project Documents | Inspection | - Procurement Management Plan
|  |  | - Assumption Log | Audits | - Schedule Baseline
|  |  | - Lessons Learned Register |  | - Cost Baseline
|  |  | - Milestone List |  | Project Documents Updates
|  |  | - Quality Reports |  | - Lessons Learned Register
|  |  | - Requirements Documentation |  | - Resource Requirements
|  |  | - Requirements Traceability Matrix |  | - Requirements Traceability Matrix
|  |  | - Risk Register |  | - Risk Register
|  |  | - Stakeholder Register |  | - Stakeholder Register
|  |  | Agreements |  | Organizational Process Assets Updates
Procurement Documentation
Approved Change Requests
Work Performance Data
Enterprise Environmental Factors
Organizational Process Assets
Stakeholder Management | Initiating | Identify Stakeholders | Project Charter | Expert Judgment | Stakeholder Register
|  |  | Business Documents | Data Gathering | Change Requests
|  |  | - Business Case | - Questionnaires & Surveys | Project Management Plan Updates
|  |  | - Benefits Management Plan | - Brainstorming | - Requirements Management Plan
|  |  | Project Management Plan | Data Analysis | - Communications Management Plan
|  |  | - Communications Management Plan | - Stakeholder Analysis | - Risk Management Plan
|  |  | - Stakeholder Engagement Plan | - Document Analysis | - Stakeholder Engagement Plan
|  |  | Project Documents | Data Representation | Project Documents Updates
|  |  | - Change Log | - Stakeholder Mapping/Representation | - Assumption Log
|  |  | - Issue Log | Meetings | - Issue Log
|  |  | - Requirements Documentation |  | - Risk Register
Agreements
Enterprise Environmental Factors
Organizational Process Assets
| Planning | Plan Stakeholder Engagement | Project Charter | Expert Judgment | Stakeholder Engagement Plan
|  |  | Project Management Plan | Data Gathering
|  |  | - Resource Management Plan | - Benchmarking
|  |  | - Communications Management Plan | Data Analysis
|  |  | - Risk Management Plan | - Assumption & Constraint Analysis
|  |  | Project Documents | - Root Cause Analysis
|  |  | - Assumption Log | Decision Making
|  |  | - Change Log | - Prioritization/Ranking
|  |  | - Issue Log | Data Representation
|  |  | - Project Schedule | - Mind Mapping
|  |  | - Risk Register | - Stakeholder Engagement Assessment Matrix
|  |  | - Stakeholder Register | Meetings
Agreements
Enterprise Environmental Factors
Organizational Process Assets
| Executing | Manage Stakeholder Engagement | Project Management Plan | Expert Judgment | Change Requests
|  |  | - Communications Management Plan | Communication Skills | Project Management Plan Updates
|  |  | - Risk Management Plan | - Feedback | - Communications Management Plan
|  |  | - Stakeholder Engagement Plan | Interpersonal & Team Skills | - Stakeholder Engagement Plan
|  |  | - Change Management Plan | - Conflict Management | Project Documents Updates
|  |  | Project Documents | - Cultural Awareness | - Change Log
|  |  | - Change Log | - Negotiation | - Issue Log
|  |  | - Issue Log | - Observation/Conversation | - Lessons Learned Register
|  |  | - Lessons Learned Register | - Political Awareness | - Stakeholder Register
|  |  | - Stakeholder Register | Ground Rules
|  |  | Enterprise Environmental Factors | Meetings
Organizational Process Assets
| M&C | Monitor Stakeholder Engagement | Project Management Plan | Data Analysis | Work Performance Information
|  |  | - Resource Management Plan | - Alternatives Analysis | Change Requests
|  |  | - Communications Management Plan | - Root Cause Analysis | Project Management Plan Updates
|  |  | - Stakeholder Engagement Plan | - Stakeholder Analysis | - Resource Management Plan
|  |  | Project Documents | Decision Making | - Communications Management Plan
|  |  | - Issue Log | - Multi-Criteria Decision Analysis | - Stakeholder Engagement Plan
|  |  | - Lessons Learned Register | - Voting | Project Documents Updates
|  |  | - Project Communications | Data Representation | - Issue Log
|  |  | - Risk Register | - Stakeholder Engagement Assessment Matrix | - Lessons Learned Register
|  |  | - Stakeholder Register | Communication Skills | - Risk Register
|  |  | Work Performance Data | - Feedback | - Stakeholder Register
|  |  | Enterprise Environmental Factors | - Presentations
|  |  | Organizational Process Assets | Interpersonal & Team Skills
- Active Listening
- Cultural Awareness
- Leadership
- Networking
- Political Awareness
Meetings

## Patterns
Here are a few patterns that can make it easier to remember the ITTOs:
ITTO Patterns
1. Inputs and outputs are often documents. Tools and techniques are often actions.
2. The “Project Management Plan” is an input to nearly every process.
3. “Org. Process Assets” and “Enterprise Environmental Factors” are inputs to most processes.
4. “Expert Judgment” and “Meetings” are tools and techniques on many processes.
5. “Project Documents Updates” is an output of most processes.
6. “PMP Updates” and “Changes Requests” are also common outputs.
7. Anything that includes “updates” will always be an output (never an input or tool).
8. Anything that includes “system” will always be a tool (never an input or output).
9. Individual plans (e.g. “Risk Mgmt. Plan”) are almost always an output of “Plan …” processes.
10. “Work Performance Data” is an input on “Monitoring” processes. (Except in “Integration”)
11. “Changes Requests” are an output on “Monitoring” processes. (Except in “Integration”)
12. “Work Performance Info.” is an output on “Monitoring” processes. (Except in “Integration”)

## Statistics
Most Common ITTOs
(in 10 or more processes)
Inputs | Processes | Tools & Techniques | Processes | Outputs | Processes
Organizational Process Assets | 47 | Expert Judgment | 35 | Project Documents Updates | 39
Project Management Plan | 47 | Data Analysis | 32 | Project Management Plan Updates | 26
Project Documents | 43 | Meetings | 28 | Change Requests | 23
Enterprise Environmental Factors | 40 | Interpersonal & Team Skills | 20 | Organizational Process Assets Updates | 10
Project Charter | 14 | Decision Making | 13 | Work Performance Information | 10
Agreements | 11 | Data Gathering | 13
Work Performance Data | 10 | Project Mgmt. Info. System | 12
|  | Data Representation | 11